## Milestones
Milestones |  | #VALUE!
Due Date
Project Coordination
Request for Training Materials Received | 2023-12-12
BRD/BUC/SOP/Other Business Documentation Reviewed
Content Creators/Authors Assigned
ClickLearn Project Team Lead Designated
Data Preparation
Verify Environment(s) to be Used for Content Creation
Verify when environment is ready to access
test
Content Development
Create Content Development List
Create Recordings/Work Instructions
Revise & Edit (InFlight to Final)
Delivery of Content to End Users
Build the Structure
Create Sections
Product & Publish the Learning Materials
Embed HTML link into the Production Environment, SharePoint, LMS
Ongoing Activities
Data Analytics Captured via Project Dashboard Analytics
Data Analyzed & Delivered to Business Stakeholders
Revise Recordings as Necessary (Releases or Ad Hoc Requests)
Maintain List of Active Authors - Cross Training
Produce & Publish the Structure
Produce then Publish using the Publishing Feature
Preview the Published Content & decide which version to be Active
Embed the URL into an application, LMS or use the Live Assist
Data Analytics
Review End User Activites from Dashboard inside ClickLearn
Request ODataFeed report
Review & Revise Content
Revise recordings as necessary when application release updates occur
Survey department heads regularly to determine if any process changes have occurred that may require updates to existing recordings or if new materials need to be created.
Review list of authors regularly to determine if any personnel changes have occurred that may require new authors to be added or others to be blocked for ongoing maintenance of learning content/materials.
Maintain List of Active Authors - Cross Training
Insert milstone, tasks and duo date, This will be added to Activities.
This workbook has been created by ClickLearn for your organization's use. Feel free to make additions or changes to it as suits your organization's needs. ClickLearn will not be held responsible for any changes or omissions that you have made to your copy of this workbook.
Questions?
Contact support here
20 min on-demand video?
See how ClickLearn works when it suits you here
Try ClickLearn for 14 days?
Get 14-days free trial and see the magic for your self here

## Activities
Content Production for XYZ Widgets
Due Date | Task | Team/member | Complete | Completion date | Comments / Updates
Project Coordination
2023-12-12 | Request for Training Materials Received
| BRD/BUC/SOP/Other Business Documentation Reviewed | Sales | Yes
| Content Creators/Authors Assigned | Finance & Accounting | No
| ClickLearn Project Team Lead Designated | Customer success |  |  | Will they be SMEs or Business Analysts, instructional designers or trainers?
|  | Management |  |  | This individual will coordinate all the recordings, created content, place into sections, build the structure, Produce & Publish the materials and make tit Public for all to give the final review before deploying to the Content Users.
Data Preparation
Verify Environment(s) to be Used for Content Creation
Verify when environment is ready to access
test
Content Development
Create Content Development List
Create Recordings/Work Instructions
Revise & Edit (InFlight to Final)
Delivery of Content to End Users
Build the Structure
Create Sections
Product & Publish the Learning Materials
Embed HTML link into the Production Environment, SharePoint, LMS
Ongoing Activities
| Data Analytics Captured via Project Dashboard Analytics | Sales |  |  | Team decides what sections to
| Data Analyzed & Delivered to Business Stakeholders | Purchasing |  |  | create, Project Team Lead creates them.
| Revise Recordings as Necessary (Releases or Ad Hoc Requests) | Inventory
| Maintain List of Active Authors - Cross Training | Finance & Accounting
Produce & Publish the Structure
| Produce then Publish using the Publishing Feature | Project TL
| Preview the Published Content & decide which version to be Active | Project TL |  |  | Project Team Lead makes it public to share
Embed the URL into an application, LMS or use the Live Assist
|  | Project TL |  |  | Team decides where to place the published content
Data Analytics
| Review End User Activites from Dashboard inside ClickLearn | Team Mbr |  |  | Any Team Member can be designated to pull metrics
Request ODataFeed report
|  | Team Mbr |  |  | Any Team Member can copy/paste the Odata Link into Power BI
Review & Revise Content
| Revise recordings as necessary when application release updates occur | Team Mbr |  |  | Use Replay function
| Survey department heads regularly to determine if any process changes have occurred that may require updates to existing recordings or if new materials need to be created. | Team Mbr |  |  | Use Record new steps or Replay function
| Review list of authors regularly to determine if any personnel changes have occurred that may require new authors to be added or others to be blocked for ongoing maintenance of learning content/materials. |  |  |  | Don't let knowledge walk due to Personnel changes! Have a back up Project Team Lead/Administrator, someone that will maintain the recordings and structure so if personnel changes, data won't be lost.
Maintain List of Active Authors - Cross Training
Last updated
XX-XX-XXXX
Prod Date
XX-XX-XXXX
Edit dates here.

## Content Development List
Content Development List | [8 empty] | #VALUE!
Work Instructions Title | Comments | Author | Date Due | Edited/ InFlight? | Ready to Move? | In the Final folder? | Added to Structure (Y/N)? | Produced & Published to Prod Environment (Date)?
Sales
Validate Account Information (sample) | Use CRM/CE, replay in Spanish | Ben | 2023-12-12 | Yes | Yes | No | Yes | 2023-12-12
Purchasing
Inventory
Finance & Accounting
Materials Maintenance
Marketing
This workbook has been created by ClickLearn for your organization's use. Feel free to make additions or changes to it as suits your organization's needs. ClickLearn will not be held responsible for any changes or omissions that you have made to your copy of this workbook.
Questions?
Contact support here
20 min on-demand video?
See how ClickLearn works when it suits you here
Try ClickLearn for 14 days?
Get 14-days free trial and see the magic for your self here

## Authors + Data settings
Authors | [6 empty] | Data settings |  | #VALUE!
| First Name | Last Name | E-Mail | Phone | Team/Department | Position | Yes / No | Departments
1 | Ben | Aflick | baf@clicklearn.com | +1 727-232.23242 | Sales | Sales Manager | Yes | Sales
2 | [6 empty] | No | Purchasing
3 | [7 empty] | Inventory
4 | [7 empty] | Finance & Accounting
5 | [7 empty] | Materials Maintenance
6 | [7 empty] | Marketing
7 | [7 empty] | Customer success
8 | [7 empty] | Project manager
9 | [7 empty] | Management
10
11
12
13
14
15
16
17
18
19
20
Fill out the content creators for each department. See example.
This workbook has been created by ClickLearn for your organization's use. Feel free to make additions or changes to it as suits your organization's needs. ClickLearn will not be held responsible for any changes or omissions that you have made to your copy of this workbook.
Questions?
Contact support here
20 min on-demand video?
See how ClickLearn works when it suits you here
Try ClickLearn for 14 days?
Get 14-days free trial and see the magic for your self here